## KNPC - CFP CRS
Kuwait National Petroleum Company (K.S.C)
Clean Fuels Project (CFP)
KNPC Contract No. CFP/EPC/0054-MAB1 ¦ PSCJ Job No. JI-2025
COMMENTS RESOLUTION SHEET
Vendor Data
Static Equipments
CAST VALVES CS AND AS < 24"
ADNOC -CODE- 2-COMMENTS-TRANSMITTAL NUMBER WF-009623
x
RIAZ AHAMED Inspection 27--07-2024
These are preliminary comments , Vendor to note drawings are not submitted and fully approved from Engineering ,Submit next revision with CRS for each points
COMPANY TPI
For valves in 3.2 following steps shall be witnessed by 3.2 TPI 1)Pouring of the cast materials 2)Sample selection 3)Heat treatment 4)Chemical, Mechanical testing -Tensile,impact , hardness testing ,IGC,PMI
CONTRACTOR TPI
VENDOR TPI FOR 3.2 CERTIFICATION
How will it be identified which valve requires 3.1 & 3.2
RW (First lot)
[Line]: ADNOC
W
[Line]: TPI
Include GAD number & Datasheet number
Provide individual sections for each type of valve
External fasteners (bolts, studs and nuts) shall be coated with PTFE or equivalent. For the details of approved coatings, refer to 1000482-ADD-SP-07-004.
CEV for butt welded valves shall be 0.42%
W
W
Mn-1.35
Address corrosion testing requirements
W
w
RT shall be in line with 1000482-ADD-SP-09-003,Rev.0 -clause-9.1
For NACE valves -ASTM supplementary requirements 4 and 5 shall apply for WFMT and RT
WFMT for NACE valves
Certain valves in this order has pup pipes at the valve ends . Vendor to details the material of pup pieces as per AGES-SP-09-003 For soft-seated valves, the pup pipes shall be welded to the valve before the valve internals are installed. The minimum pup piece length shall be as per Attachment -3 of 1000482-ADD-1300-185 Welded ends valves shall be tested along with pup pieces Vendor shall provide test rings (500mm long) from pup piece Carbon content of butt-welding CS bodies shall be limited to 0.25 % max. The CEV by check analysis shall not exceed 0.42 %.material for field weld procedure qualification in case pup piece is of forged execution. RT and MPI shall be done for the welding between pup pipie and valve ,WPS/PQR shall be submitted for review and approval PWHT applicability as per WPS/PQR
RW
w
w
w
w
Specify where the welding is involved in cast valves
If weld overlay is applicable identify it along with the testings
Vendor shall table all the list of valves as per PO with data sheet number , NACE requiements , material certification 3.1/3.2 and type of valves ,MDMT temperature ,cryogenic valves, vacuum valves
Vendor to specify testing requirements for gate , globe and check valves seperately
RW RW
w
w
w
w
w
w
Vacum test is required for all the valves required as per valve data sheet any conflicts shall be approved from JV Engineering
Vendor to confirm cryogenic test is applicability as the drawings are still in approval
FET requirment to be added to this list
[Line]: (if
[Line]: required on purchase
[Line]: order)
RW
[Line]: W W W
w
w
w
w
Add load test for the valve weight greater than 250 kg
Add stage for Issuance of Inspection Release Note
ADD MTC review for 3.2 /3.1 certification for the valves
SS Tag plate of the valve shall indicate the name of the manufacturer, model no., serial no., size, rating, service, certification data and valve datasheet no. In addition - One additional name plate shall be supplied loosely together with valve for insulated valves.
Valves shall have a position indicator showing open and closed positions
The Globe valve shall be shipped with the obturator in closed position. Globe Valves shall have the glands and spindles shrouded by a wrapping of petroleum tape around the valve yoke.
Valves shall have facilities for provision of padlock at site and for locking in the fully open and fully closed positions.
Flow direction shall be permanent on the valves Heat number for the castings shall be permanently marked on the valve body.
The Criticality Rating is: 1 and the Inspection Class is: 1 in these cases: A. All services: 600# and above for all sizes, ; 300# 18” and above. B. Critical Service (Sour/Cryogenic/Amine/Steam): CS/ LTCS ≥ 6” and / or ≥ 150# C. CRA valves Critical service (Sour /Cryogenic): all sizes D. CRA Non sour (e g Chemical injection, Utility, etc) for sizes > 4” E. Valves for TSO, Hot Tap, stoppling: all sizes and ratings F. Valves in Cyclic Service: all sizes and ratings The Criticality Rating is: 2 and the Inspection Class is: 2 in other rating & sizes not covered above.
Original Document Title : ITP-Fabrication, Erection & Testing of A/G & u/G welded pipe |  |  | COMPANY's Review Comments Transmittal No. : CFP-TR-0042 |  | Date : 15-May-2025 | Date : 15-May-2025
Serial No. | Document No., Rev, Page No. | COMPANY's COMMENT | Action Code (*) | CONTRACTOR RESPONSE (**) | COMPANY's Response (Open or Closed)
1 | Pg 8 &9 | Serial 1.2, 1.4, 1.5, 1.6, 1.7, 1.10 & 1.11 | A | Noted and Incorporated | Closed
2 | Pg 10 | RT Film Interpretation | A | On Regular basis | Closed
3 | Pg 11 | Serial 1.9 | A | Points included (CV, Level 2 certificates and Skill Test) | Closed
4 | Pg 13 | Serial 1.15 (Check pipe support & Anchor position) | A | Removed | Closed
5 | Pg 15,16.18 | Serial 1.16, 2.2, 2.5, 2.7, 2.8, 2.9, & 2.14 | A | Noted and Incorporated | Closed
6 | Pg 18 | Serial 2.13 ( Piping alignment & Dimension Check) | A | Removed | Closed
7 | Pg 18 | Serial 2.14 (Bolt Tensioning) | A | Included as commented | Closed
8 | Pg 18 | Serial 2.15 (RF pad test for Branch connection) | A | Included | Closed
9 | Pg 20 – Pg 25 | Section 3 (Serial 3.1 to 3.19) | A | Removed and incorporated in Section 2 | Closed
10 | Pg 26 to Pg 29 | Section 4 (Serial 4.1 to 4.18) | A | Removed and incorporated in Section 2 & Section 3 | Closed
11
12
Action Code: A-Accepted, N-Not accepted (*) To be completed by Contractor (**) To be completed by Contractor if action code is 'N'
SIGNED BY CONTRACTOR |  |  | SIGNED BY COMPANY
Prepared By (Name): Signature: |  | Date : | Approved by (Name): Signature: |  | Date :
Approved By (Name): Signature: |  | Date : | Reviewed / Accepted by (Name): Signature: |  | Date :