## Comments Resolution Sheet
CLIENT LOGO & NAME HERE |  |  |  | Comments Resolution Sheet |  |  |  | CONTRACTOR LOGO AND NAME HERE
PROJECT NAME HERE |  |  |  | Company Project No. |  | Project No. | Doc. Class |  | Distribution Code
Company Doc. No. |  | Not Applicable |  | Doc. No. |  |  | Rev. |  | Page
Document Title |  |  |  |  | Doc. Reference No. |  |  |  |  | Rev.
[5 empty] | CLIENT: |  | CONTRACTOR:
Sr. No. | Document / Drawing Section |  | CLIENT / Comments |  |  | Contractor's Response |  |  | Final Resolution (XXXXX)
1 | Page 1 |  | Vendor Data
2 | Page 1 |  | Static Equipments
3 | Page 1 |  | CAST VALVES CS AND AS < 24"
4 | Page 1 |  | ADNOC -CODE- 2-COMMENTS-TRANSMITTAL NUMBER WF-009623
5 | Page 1 |  | x
6 | Page 1 |  | RIAZ AHAMED Inspection 27--07-2024
7 | Page 1 |  | These are preliminary comments , Vendor to note drawings are not submitted and fully approved from Engineering ,Submit next revision with CRS for each points
8 | Page 2 |  | COMPANY TPI
9 | Page 2 |  | For valves in 3.2 following steps shall be witnessed by 3.2 TPI 1)Pouring of the cast materials 2)Sample selection 3)Heat treatment 4)Chemical, Mechanical testing -Tensile,impact , hardness testing ,IGC,PMI
10 | Page 2 |  | CONTRACTOR TPI
11 | Page 2 |  | VENDOR TPI FOR 3.2 CERTIFICATION
12 | Page 2 |  | How will it be identified which valve requires 3.1 & 3.2
13 | Page 2 |  | RW (First lot)
14 | Page 2 |  | [Line]: ADNOC
15 | Page 2 |  | W
16 | Page 2 |  | [Line]: TPI
17 | Page 2 |  | Include GAD number & Datasheet number
18 | Page 2 |  | Provide individual sections for each type of valve
19 | Page 3 |  | External fasteners (bolts, studs and nuts) shall be coated with PTFE or equivalent. For the details of approved coatings, refer to 1000482-ADD-SP-07-004.
20 | Page 3 |  | CEV for butt welded valves shall be 0.42%
21 | Page 3 |  | W
22 | Page 3 |  | W
23 | Page 3 |  | Mn-1.35
24 | Page 3 |  | Address corrosion testing requirements
25 | Page 4 |  | W
26 | Page 4 |  | w
27 | Page 4 |  | RT shall be in line with 1000482-ADD-SP-09-003,Rev.0 -clause-9.1
28 | Page 4 |  | For NACE valves -ASTM supplementary requirements 4 and 5 shall apply for WFMT and RT
29 | Page 4 |  | WFMT for NACE valves
30 | Page 5 |  | Certain valves in this order has pup pipes at the valve ends . Vendor to details the material of pup pieces as per AGES-SP-09-003 For soft-seated valves, the pup pipes shall be welded to the valve before the valve internals are installed. The minimum pup piece length shall be as per Attachment -3 of 1000482-ADD-1300-185 Welded ends valves shall be tested along with pup pieces Vendor shall provide test rings (500mm long) from pup piece Carbon content of butt-welding CS bodies shall be limited to 0.25 % max. The CEV by check analysis shall not exceed 0.42 %.material for field weld procedure qualification in case pup piece is of forged execution. RT and MPI shall be done for the welding between pup pipie and valve ,WPS/PQR shall be submitted for review and approval PWHT applicability as per WPS/PQR
31 | Page 5 |  | RW
32 | Page 5 |  | w
33 | Page 5 |  | w
34 | Page 5 |  | w
35 | Page 5 |  | w
36 | Page 5 |  | Specify where the welding is involved in cast valves
37 | Page 5 |  | If weld overlay is applicable identify it along with the testings
38 | Page 6 |  | Vendor shall table all the list of valves as per PO with data sheet number , NACE requiements , material certification 3.1/3.2 and type of valves ,MDMT temperature ,cryogenic valves, vacuum valves
39 | Page 6 |  | Vendor to specify testing requirements for gate , globe and check valves seperately
40 | Page 6 |  | RW RW
41 | Page 6 |  | w
42 | Page 6 |  | w
43 | Page 6 |  | w
44 | Page 6 |  | w
45 | Page 6 |  | w
46 | Page 6 |  | w
47 | Page 6 |  | Vacum test is required for all the valves required as per valve data sheet any conflicts shall be approved from JV Engineering
48 | Page 6 |  | Vendor to confirm cryogenic test is applicability as the drawings are still in approval
49 | Page 6 |  | FET requirment to be added to this list
50 | Page 6 |  | [Line]: (if
51 | Page 6 |  | [Line]: required on purchase
52 | Page 6 |  | [Line]: order)
53 | Page 7 |  | RW
54 | Page 7 |  | [Line]: W W W
55 | Page 7 |  | w
56 | Page 7 |  | w
57 | Page 7 |  | w
58 | Page 7 |  | w
59 | Page 7 |  | Add load test for the valve weight greater than 250 kg
60 | Page 7 |  | Add stage for Issuance of Inspection Release Note
61 | Page 7 |  | ADD MTC review for 3.2 /3.1 certification for the valves
62 | Page 8 |  | SS Tag plate of the valve shall indicate the name of the manufacturer, model no., serial no., size, rating, service, certification data and valve datasheet no. In addition - One additional name plate shall be supplied loosely together with valve for insulated valves.
63 | Page 8 |  | Valves shall have a position indicator showing open and closed positions
64 | Page 8 |  | The Globe valve shall be shipped with the obturator in closed position. Globe Valves shall have the glands and spindles shrouded by a wrapping of petroleum tape around the valve yoke.
65 | Page 8 |  | Valves shall have facilities for provision of padlock at site and for locking in the fully open and fully closed positions.
66 | Page 8 |  | Flow direction shall be permanent on the valves Heat number for the castings shall be permanently marked on the valve body.
67 | Page 8 |  | The Criticality Rating is: 1 and the Inspection Class is: 1 in these cases: A. All services: 600# and above for all sizes, ; 300# 18” and above. B. Critical Service (Sour/Cryogenic/Amine/Steam): CS/ LTCS ≥ 6” and / or ≥ 150# C. CRA valves Critical service (Sour /Cryogenic): all sizes D. CRA Non sour (e g Chemical injection, Utility, etc) for sizes > 4” E. Valves for TSO, Hot Tap, stoppling: all sizes and ratings F. Valves in Cyclic Service: all sizes and ratings The Criticality Rating is: 2 and the Inspection Class is: 2 in other rating & sizes not covered above.
Add additional as required
Comments Approved by Company / CLIENT |  |  |  | Response to Company / Comments |  |  | Final Resolution Approved by Company / CLIENT
Name |  |  |  | Name |  |  | Name
Signature |  |  |  | Signature |  |  | Signature
Position |  |  |  | Position |  |  | Position
Party |  |  |  | Party |  |  | Party
Date |  |  |  | Date |  |  | Date