## KNPC - CFP CRS
Kuwait National Petroleum Company (K.S.C)
Clean Fuels Project (CFP)
KNPC Contract No. CFP/EPC/0054-MAB1 ¦ PSCJ Job No. JI-2025
COMMENTS RESOLUTION SHEET
Discipline : Mechanical |  |  | Sub-contractor / Vendor Document No.: P6012MAB.000.10.03.459
Original Document Title : ITP-Fabrication, Erection & Testing of A/G & u/G welded pipe |  |  | COMPANY's Review Comments Transmittal No. : CFP-TR-0042 |  | Date : 15-May-2025 | Date : 15-May-2025
Serial No. | Document No., Rev, Page No. | COMPANY's COMMENT | Action Code (*) | CONTRACTOR RESPONSE (**) | COMPANY's Response (Open or Closed)
1 | Pg 8 &9 | Serial 1.2, 1.4, 1.5, 1.6, 1.7, 1.10 & 1.11 | A | Noted and Incorporated | Closed
2 | Pg 10 | RT Film Interpretation | A | On Regular basis | Closed
3 | Pg 11 | Serial 1.9 | A | Points included (CV, Level 2 certificates and Skill Test) | Closed
4 | Pg 13 | Serial 1.15 (Check pipe support & Anchor position) | A | Removed | Closed
5 | Pg 15,16.18 | Serial 1.16, 2.2, 2.5, 2.7, 2.8, 2.9, & 2.14 | A | Noted and Incorporated | Closed
6 | Pg 18 | Serial 2.13 ( Piping alignment & Dimension Check) | A | Removed | Closed
7 | Pg 18 | Serial 2.14 (Bolt Tensioning) | A | Included as commented | Closed
8 | Pg 18 | Serial 2.15 (RF pad test for Branch connection) | A | Included | Closed
9 | Pg 20 – Pg 25 | Section 3 (Serial 3.1 to 3.19) | A | Removed and incorporated in Section 2 | Closed
10 | Pg 26 to Pg 29 | Section 4 (Serial 4.1 to 4.18) | A | Removed and incorporated in Section 2 & Section 3 | Closed
11
12
Action Code: A-Accepted, N-Not accepted (*) To be completed by Contractor (**) To be completed by Contractor if action code is 'N'
SIGNED BY CONTRACTOR |  |  | SIGNED BY COMPANY
Prepared By (Name): Signature: |  | Date : | Approved by (Name): Signature: |  | Date :
Approved By (Name): Signature: |  | Date : | Reviewed / Accepted by (Name): Signature: |  | Date :