## Standard CRS
Comment Response Sheet
Company | : |  |  | Doc No. : ENG-CRS-2025-001
Project Title | : |  |  | Doc. Title : P&ID Detailed Design Review
|  |  |  | Doc. No. : DWG-001-A |  | Rev: B
PO No. | :
No. | Section | Comment | Response | Commented by | Date | Status O/C * | Remarks
1 | Sec 2.1 | Verify design pressure rating for high-pressure bypass line. | Updated design pressure from 15 bar to 20 bar in P&ID sheet 3. | J. Doe | 2025-06-01 | C | Verified
2 | Sec 4.3 | Provide vendor catalog cuts for emergency isolation valves. | Vendor data sheets attached in Appendix D for review. | A. Smith | 2025-06-01 | C | Ready for signoff
3 | Sec 5.0 | Confirm material compatibility with sour gas service (NACE MR0175). | Material specification updated to Inconel 625 cladding. | M. AL-Sabah | 2025-06-03 | O | Pending lab test
4 |  |  |  | -
5 |  |  |  | -
6
7
8
* Status: O = Open, C = Closed