## Architectural & Interiors CRS
ORO INTERIORS ¦ Comments Resolution Sheet (CRS)
Project Number | Project Name
PRJ-2025-089 | Luxury Residential Villa - Penthouse Fit-Out
Discipline | Drawing Number | Drawing Title | Date | Revision
Interior Architecture | INT-WD-102 | Master Bedroom & Walk-in Closet Joinery Details | 2025-05-18 | Rev 02
# | Comment |  | Response
1 | Adjust wardrobe internal LED strip recess to 15mm with frosted diffuser. |  | Updated in detail callout 3 on Sheet 4; recess depth set to 15mm.
2 | Clarify veneer finish code for headboard feature wall panels. |  | Specified American Walnut Crown Cut - Code VN-04 with matte PU lacquer.
3 | Coordinate false ceiling drop height with MEP AC duct clash at bedroom entry. |  | Ceiling lowered by 50mm locally as per coordinated MEP drawing REV-C.
4 | Confirm soft-close concealed hinge brand and model for dressing unit shutters. |  | Blum Clip-Top BLUMOTION 110-degree hinges incorporated in joinery specs.
5 | Add skirting detail along wardrobe toe kick with bronze shadow gap. |  | Detail added to Section B-B on drawing INT-WD-102.
6
7
8
9
10